## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Booking
Program Manager | Aldina Kurtović, Elmedina Marić, Nejra Topić
Project Manager | Aldina Kurtović, Elmedina Marić, Nejra Topić
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2026-01-07 | Nejra Topić | Neosvježavanje rezultata pretrage (listinga) nakon promjene filtera cijene u podsistemu Filtriranja Smještaja. Steps to Reproduce 1. Open the Booking Application web browser. 2. On the Home Page, execute a search for accommodation (location, dates). 3. Search Results page is shown. 4. In the Filters sidebar, drag the slider or manually change the Price Range filter (e.g., from 50€-500€ to 100€-200€). 5. DO NOT click the main "Search" button again. 6. Observe the list of accommodations. Expected Result The search results list should automatically refresh and display only accommodations that fall within the newly set price range. | Executing/Controlling | Testing | High | Developer | 2026-01-07 | 1 hour | New | Implementiran event listener na promjenu raspona cijena koji automatski poziva funkciju osvježavanja rezultata pretrage (Search API). | 2026-01-08 | 1 hour | Bad Code (Missing event handling logic) | New
2 | 2026-01-07 | Nejra Topić | 1.Navigate to the Home Page search form. 2. Open the Calendar control for date selection. 3. Select a Date of Departure (e.g., February 15th, 2026). 4. Select a Date of Arrival (e.g., February 10th, 2026)—a date that is earlier than the selected departure date. 5. Confirm the selection. Expected Result The calendar should prevent the selection in step 4 (Date of Arrival should be less than or equal to Date of Departure) and display a clear error message (e.g., "Departure date cannot precede arrival date"). | Executing/Controlling | Testing | High | Developer | 2026-01-08 | 2 hours | Completed | Dodana if-else logika validacije datuma na klijentskoj strani koja sprječava odabir datuma odlaska ranijeg od datuma dolaska. | 2026-01-08 | 1.5 hours | Bad Code (Missing data validation) | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2026-01-07 | Nejra Topić | Ukupna cijena ne uključuje takse na rezervaciju u podsistemu Plaćanja/Rezervacije. Steps to Reproduce 1. Execute a full search and navigate to the final "Payment Confirmation" page. 2. The page displays a breakdown: Accommodation Price (e.g., 300€), Local Taxes/Fees (e.g., 30€), Service Fee (e.g., 10€). 3. Observe the final line: "Total Price". 4. Manually sum the individual price components (300€ + 30€ + 10€ = 340€). 5. Compare the manual sum with the "Total Price" displayed. Expected Result The "Total Price" displayed (e.g., 340€) must be exactly equal to the sum of all individual price components, including taxes and fees. | Executing/Controlling | Development | High | Backend Lead | 2026-01-08 | 4 hours | In Progress | Ispravljena back-end funkcija za izračun cijene (calculateTotal) kako bi ispravno uključila sve lokalne takse i provizije iz baze podataka prije slanja klijentu. | 2026-01-10 | 3 hours | Oversight (Lack of detailed code review on integration) | In Progress | Medium | Initiating | Concept
4 | 2026-01-07 | Nejra Topić | Tipka za povratak (Back Button) na Detaljima smještaja vraća na početnu stranicu umjesto na listu rezultata. Steps to Reproduce 1. Execute a search for accommodation. 2. Search Results page is shown (List of results). 3. Click on a specific accommodation to view the details (e.g., navigate to "Apartment Details" page). 4. Use the browser's "Back" button (or the application's internal "Back to results" button). Expected Result The user should be returned to the immediately preceding page (the Search Results list), maintaining the applied filters and scroll position. | Executing/Controlling | Testing | Medium | Developer | 2026-01-09 | 1 hour | New | Ažurirana front-end router konfiguracija (ili korištenje window.history.back()) kako bi se osiguralo da Back Button navigira na prethodno spremljenu listu rezultata. | 2026-01-12 | 1 hour | Bad Code (Faulty routing configuration) | Completed | Low | Planning | Requirements
5 | 2026-01-07 | Nejra Topić | Nazivi mjeseci u kalendaru ostaju na engleskom jeziku iako je odabran lokalni jezik (Lokalizacija). Steps to Reproduce 1. Log in (optional, but recommended). 2. Change the application language setting to a non-English language (e.g., "Hrvatski", "Njemački", "Francuski"). 3. Navigate to the Home Page search form. 4. Open the Calendar control for date selection. Expected Result All elements within the calendar, including the names of the months (e.g., "Siječanj" umjesto "January"), should be displayed in the language selected in Step 2. | Executing/Controlling | Testing | Medium | Developer | 2026-01-09 | 3 hours | Under Review | Otklonjen bug u lokalizacijskoj biblioteci; osigurano je da komponenta kalendara ispravno dohvaća prevedene nazive mjeseca iz .json resurs fajlova za odabrani jezik. | 2026-01-13 | 5 hours | Oversight (Incomplete localization testing) |  |  | Executing/Controlling | Design
6 | 2026-01-07 | Aldina Kurtović | U podsistemu Registracije korisnika, sistem ne prikazuje jasnu i korisniku razumljivu poruku greške prilikom pokušaja registracije sa već postojećom e-mail adresom. Forma se resetuje ili ostaje u istom stanju bez ikakvog obavještenja o uzroku neuspješne registracije, što dovodi do konfuzije korisnika i narušava korisničko iskustvo. | Executing/Controlling | Testing | Medium | Development Team | 2026-07-01 | 2 hours | New | Implementirati jasnu validacijsku poruku koja korisniku informiše da je e-mail adresa već registrovana te ponuditi opcije prijave ili resetovanja lozinke. | 10.1.2026 | 2 hours | Nedostaje korisnički feedback i validacija |  |  | Closing | Development
7 | 2026-01-07 | Elmedina Marić | Marić Sistem dozvoljava višestruke pokušaje registracije sa istom e-mail adresom bez ikakvog ograničenja ili blokade, što može dovesti do nepotrebnog opterećenja sistema i lošeg korisničkog iskustva. | Executing/Controlling | Testing | Low | Development Team | 2026-08-02 | 1.5 hours | New | Ograničiti broj pokušaja registracije sa istom e-mail adresom i jasno informisati korisnika o narednim koracima. | 1900-01-07 | 2 hours | Nedostaje kontrola poslovnih pravila |  |  |  | Testing
8 | 2026-01-07 | Aldina Kurtović | Nakon promjene jezika aplikacije, pojedini elementi korisničkog interfejsa (npr. dugmad i opisi filtera) ostaju na prethodno odabranom jeziku. Ovakvo ponašanje dovodi do djelimične lokalizacije sistema i negativno utiče na korisničko iskustvo. | Executing/Controlling | Testing | Medium | Development Team | 2026-08-01 | 3 hours | Under Review | Osigurati pravilno čuvanje izmjena korisničkih podataka u bazi i učitavanje ažuriranih podataka prilikom ponovne prijave. | 2026-10-01 | 3 hours | Nedostaje verifikacija perzistencije podataka |  |  |  | Documentation and Training
9 | 2026-01-07 | Elmedina Marić | Prilikom povratka na stranicu rezultata pretrage nakon pregleda detalja smještaja, prethodno primijenjeni filteri (cijena, ocjena, lokacija) nisu sačuvani i resetuju se na početne vrijednosti. Ovo ponašanje otežava korisnicima nastavak pretrage i narušava kontinuitet korisničkog iskustva. | Executing/Controlling | Testing | Medium | Development Team | 2026-08-01 | 2 hours | Under Review | Dodati provjeru uspješnosti transakcije i osigurati da se podaci učitavaju iz ažuriranog izvora. | 2026-10-01 | 3 hours | Database transaction not committed |  |  |  | Deployment
10 | 01/08/106 | [16 empty] | Post-Deployment
11 | 01/08/116
12 | 01/08/126
13 | 01/08/136
14 | 01/08/146
15 | 01/08/156
16 | 01/08/166
17 | 01/08/176
18 | 01/08/186
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).